## Original
JPMC GFBM Virtual Experience Program
Task 1 - Data Analysis
Hypothetical Project Cost - Budget vs. Actual
|  |  |  | Budget Hours | [5 empty] | Actual Hours | [5 empty] | Budget Cost | [5 empty] | Actual Cost
Project | Task | Resource | Cost $ / hr | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6
Project A | AT1 | Gail | 50 | 20 | 20 | 20 | 20 | 20 | 20 | 24 | 24 | 24 | 30 | 30 | 30 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500
Project A | AT1 | Tom | 35 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 90 | 90 | 90 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 3150 | 3150 | 3150
Project A | AT1 | Jenny | 75 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000
Project A | AT1 | Monique | 105 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100
Project A | AT1 | Jim | 90 | 140 | 140 | 140 | 140 | 140 | 140 | 160 | 160 | 160 | 160 | 160 | 160 | 12600 | 12600 | 12600 | 12600 | 12600 | 12600 | 14400 | 14400 | 14400 | 14400 | 14400 | 14400
Project A | AT2 | Gail | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500
Project A | AT2 | Monique | 105 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100
Project A | AT3 | Gail | 50 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000
Project A | AT3 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600
Project B | BT1 | Gail | 50 | 20 | 20 | 20 | 20 | 20 | 20 | 24 | 24 | 24 | 24 | 24 | 24 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200
Project B | BT1 | Jenny | 75 | 40 | 40 | 40 | 40 | 40 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3750 | 3750 | 3750 | 3750 | 3750 | 3750
Project B | BT1 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600
Project B | BT2 | Gail | 50 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250
Project B | BT2 | Monique | 105 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200
Project B | BT2 | Erica | 140 | 40 | 40 | 40 | 40 | 40 | 40 | 50 | 50 | 50 | 25 | 25 | 25 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 7000 | 7000 | 7000 | 3500 | 3500 | 3500
Project B | BT3 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600
Project B | BT3 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500
Project B | BT3 | Erica | 140 | 40 | 40 | 40 | 40 | 40 | 40 | 50 | 50 | 50 | 25 | 25 | 25 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 7000 | 7000 | 7000 | 3500 | 3500 | 3500
Project C | CT1 | Gail | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 5 | 5 | 5 | 5 | 5 | 500 | 500 | 500 | 500 | 500 | 500 | 250 | 250 | 250 | 250 | 250 | 250
Project C | CT1 | Tom | 35 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800
Project C | CT1 | Jenny | 75 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000
Project C | CT1 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500
Project C | CT2 | Monique | 105 | 80 | 80 | 80 | 80 | 80 | 80 | 120 | 120 | 120 | 120 | 120 | 120 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 12600 | 12600 | 12600 | 12600 | 12600 | 12600
Project C | CT2 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600
Project C | CT2 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500
Project C | CT3 | Gail | 50 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500
Project C | CT3 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600
Project C | CT3 | Erica | 140 | 40 | 40 | 40 | 40 | 40 | 40 | 50 | 50 | 50 | 25 | 25 | 25 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 7000 | 7000 | 7000 | 3500 | 3500 | 3500
Project C | CT4 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600
Project C | CT4 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500
Project C | CT5 | Erica | 140 | 40 | 40 | 40 | 40 | 40 | 40 | 50 | 50 | 50 | 25 | 25 | 25 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 7000 | 7000 | 7000 | 3500 | 3500 | 3500
Project C | CT5 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600
Project D | DT1 | Jim | 90 | 20 | 20 | 20 | 20 | 20 | 20 | 15 | 15 | 15 | 15 | 15 | 15 | 1800 | 1800 | 1800 | 1800 | 1800 | 1800 | 1350 | 1350 | 1350 | 1350 | 1350 | 1350
Project D | DT1 | Inigo | 95 | 160 | 160 | 160 | 160 | 160 | 160 | 110 | 110 | 110 | 110 | 110 | 110 | 15200 | 15200 | 15200 | 15200 | 15200 | 15200 | 10450 | 10450 | 10450 | 10450 | 10450 | 10450
Project D | DT1 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500
Project D | DT1 | Crystal | 120 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600
Project D | DT2 | Sarah | 75 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000
Project D | DT2 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600
Project D | DT2 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500
Project D | DT2 | Crystal | 120 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600
Project D | DT3 | Sarah | 75 | 80 | 80 | 80 | 80 | 80 | 80 | 90 | 90 | 90 | 90 | 90 | 90 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6750 | 6750 | 6750 | 6750 | 6750 | 6750
Project D | DT3 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600
Project D | DT3 | Crystal | 120 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600
Project D | DT4 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600
Project D | DT4 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500
Project D | DT4 | Crystal | 120 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600
Project E | ET1 | Gail | 50 | 40 | 40 | 40 | 40 | 40 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500
Project E | ET1 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600
Project E | ET1 | Crystal | 120 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600
Project E | ET2 | Sondra | 45 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200
Project E | ET2 | Larry | 88 | 160 | 160 | 160 | 160 | 160 | 160 | 80 | 80 | 80 | 80 | 80 | 80 | 14080 | 14080 | 14080 | 14080 | 14080 | 14080 | 7040 | 7040 | 7040 | 7040 | 7040 | 7040
Project E | ET2 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600
Project E | ET2 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500

## Main
Project | Task | Resource | Cost $ / hr | BH Month 1 | BH Month 2 | BH Month 3 | BH Month 4 | BH Month 5 | BH Month 6 | AH Month 1 | AH Month 2 | AH Month 3 | AH Month 4 | AH Month 5 | AH Month 6 | BC Month 1 | BC Month 2 | BC Month 3 | BC Month 4 | BC Month 5 | BC Month 6 | AC Month 1 | AC Month 2 | AC Month 3 | AC Month 4 | AC Month 5 | AC Month 6 | Total Budgeted Cost | Total Actual Cost | Difference | Total BH | Total AH | Total Hour Difference
Project A | AT1 | Gail | 50 | 20 | 20 | 20 | 20 | 20 | 20 | 24 | 24 | 24 | 30 | 30 | 30 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 6000 | 8100 | 2100 | 120 | 162 | 42
Project A | AT1 | Tom | 35 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 90 | 90 | 90 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 3150 | 3150 | 3150 | 16800 | 17850 | 1050 | 480 | 510 | 30
Project A | AT1 | Jenny | 75 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 18000 | 18000 | 0 | 240 | 240 | 0
Project A | AT1 | Monique | 105 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 12600 | 12600 | 0 | 120 | 120 | 0
Project A | AT1 | Jim | 90 | 140 | 140 | 140 | 140 | 140 | 140 | 160 | 160 | 160 | 160 | 160 | 160 | 12600 | 12600 | 12600 | 12600 | 12600 | 12600 | 14400 | 14400 | 14400 | 14400 | 14400 | 14400 | 75600 | 86400 | 10800 | 840 | 960 | 120
Project A | AT2 | Gail | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 3000 | 3000 | 0 | 60 | 60 | 0
Project A | AT2 | Monique | 105 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 12600 | 12600 | 0 | 120 | 120 | 0
Project A | AT3 | Gail | 50 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 6000 | 6000 | 0 | 120 | 120 | 0
Project A | AT3 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600 | 3000 | 3600 | 600 | 60 | 72 | 12
Project B | BT1 | Gail | 50 | 20 | 20 | 20 | 20 | 20 | 20 | 24 | 24 | 24 | 24 | 24 | 24 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 6000 | 7200 | 1200 | 120 | 144 | 24
Project B | BT1 | Jenny | 75 | 40 | 40 | 40 | 40 | 40 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3750 | 3750 | 3750 | 3750 | 3750 | 3750 | 18000 | 22500 | 4500 | 240 | 300 | 60
Project B | BT1 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600 | 3000 | 3600 | 600 | 60 | 72 | 12
Project B | BT2 | Gail | 50 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 1500 | 1500 | 0 | 30 | 30 | 0
Project B | BT2 | Monique | 105 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 25200 | 25200 | 0 | 240 | 240 | 0
Project B | BT2 | Erica | 140 | 40 | 40 | 40 | 40 | 40 | 40 | 50 | 50 | 50 | 25 | 25 | 25 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 7000 | 7000 | 7000 | 3500 | 3500 | 3500 | 33600 | 31500 | -2100 | 240 | 225 | -15
Project B | BT3 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600 | 3000 | 3600 | 600 | 60 | 72 | 12
Project B | BT3 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 7200 | 9000 | 1800 | 120 | 150 | 30
Project B | BT3 | Erica | 140 | 40 | 40 | 40 | 40 | 40 | 40 | 50 | 50 | 50 | 25 | 25 | 25 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 7000 | 7000 | 7000 | 3500 | 3500 | 3500 | 33600 | 31500 | -2100 | 240 | 225 | -15
Project C | CT1 | Gail | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 5 | 5 | 5 | 5 | 5 | 500 | 500 | 500 | 500 | 500 | 500 | 250 | 250 | 250 | 250 | 250 | 250 | 3000 | 1500 | -1500 | 60 | 30 | -30
Project C | CT1 | Tom | 35 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 16800 | 16800 | 0 | 480 | 480 | 0
Project C | CT1 | Jenny | 75 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 36000 | 36000 | 0 | 480 | 480 | 0
Project C | CT1 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 7200 | 9000 | 1800 | 120 | 150 | 30
Project C | CT2 | Monique | 105 | 80 | 80 | 80 | 80 | 80 | 80 | 120 | 120 | 120 | 120 | 120 | 120 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 12600 | 12600 | 12600 | 12600 | 12600 | 12600 | 50400 | 75600 | 25200 | 480 | 720 | 240
Project C | CT2 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600 | 3000 | 3600 | 600 | 60 | 72 | 12
Project C | CT2 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 7200 | 9000 | 1800 | 120 | 150 | 30
Project C | CT3 | Gail | 50 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 9000 | 9000 | 0 | 180 | 180 | 0
Project C | CT3 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600 | 3000 | 3600 | 600 | 60 | 72 | 12
Project C | CT3 | Erica | 140 | 40 | 40 | 40 | 40 | 40 | 40 | 50 | 50 | 50 | 25 | 25 | 25 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 7000 | 7000 | 7000 | 3500 | 3500 | 3500 | 33600 | 31500 | -2100 | 240 | 225 | -15
Project C | CT4 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600 | 3000 | 3600 | 600 | 60 | 72 | 12
Project C | CT4 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 7200 | 9000 | 1800 | 120 | 150 | 30
Project C | CT5 | Erica | 140 | 40 | 40 | 40 | 40 | 40 | 40 | 50 | 50 | 50 | 25 | 25 | 25 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 7000 | 7000 | 7000 | 3500 | 3500 | 3500 | 33600 | 31500 | -2100 | 240 | 225 | -15
Project C | CT5 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600 | 3000 | 3600 | 600 | 60 | 72 | 12
Project D | DT1 | Jim | 90 | 20 | 20 | 20 | 20 | 20 | 20 | 15 | 15 | 15 | 15 | 15 | 15 | 1800 | 1800 | 1800 | 1800 | 1800 | 1800 | 1350 | 1350 | 1350 | 1350 | 1350 | 1350 | 10800 | 8100 | -2700 | 120 | 90 | -30
Project D | DT1 | Inigo | 95 | 160 | 160 | 160 | 160 | 160 | 160 | 110 | 110 | 110 | 110 | 110 | 110 | 15200 | 15200 | 15200 | 15200 | 15200 | 15200 | 10450 | 10450 | 10450 | 10450 | 10450 | 10450 | 91200 | 62700 | -28500 | 960 | 660 | -300
Project D | DT1 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 7200 | 9000 | 1800 | 120 | 150 | 30
Project D | DT1 | Crystal | 120 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 21600 | 21600 | 0 | 180 | 180 | 0
Project D | DT2 | Sarah | 75 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 36000 | 36000 | 0 | 480 | 480 | 0
Project D | DT2 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600 | 3000 | 3600 | 600 | 60 | 72 | 12
Project D | DT2 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 7200 | 9000 | 1800 | 120 | 150 | 30
Project D | DT2 | Crystal | 120 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 21600 | 21600 | 0 | 180 | 180 | 0
Project D | DT3 | Sarah | 75 | 80 | 80 | 80 | 80 | 80 | 80 | 90 | 90 | 90 | 90 | 90 | 90 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6750 | 6750 | 6750 | 6750 | 6750 | 6750 | 36000 | 40500 | 4500 | 480 | 540 | 60
Project D | DT3 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600 | 3000 | 3600 | 600 | 60 | 72 | 12
Project D | DT3 | Crystal | 120 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 21600 | 21600 | 0 | 180 | 180 | 0
Project D | DT4 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600 | 3000 | 3600 | 600 | 60 | 72 | 12
Project D | DT4 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 7200 | 9000 | 1800 | 120 | 150 | 30
Project D | DT4 | Crystal | 120 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 21600 | 21600 | 0 | 180 | 180 | 0
Project E | ET1 | Gail | 50 | 40 | 40 | 40 | 40 | 40 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 12000 | 15000 | 3000 | 240 | 300 | 60
Project E | ET1 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600 | 3000 | 3600 | 600 | 60 | 72 | 12
Project E | ET1 | Crystal | 120 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 21600 | 21600 | 0 | 180 | 180 | 0
Project E | ET2 | Sondra | 45 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 43200 | 43200 | 0 | 960 | 960 | 0
Project E | ET2 | Larry | 88 | 160 | 160 | 160 | 160 | 160 | 160 | 80 | 80 | 80 | 80 | 80 | 80 | 14080 | 14080 | 14080 | 14080 | 14080 | 14080 | 7040 | 7040 | 7040 | 7040 | 7040 | 7040 | 84480 | 42240 | -42240 | 960 | 480 | -480
Project E | ET2 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 500 | 500 | 500 | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600 | 3000 | 3600 | 600 | 60 | 72 | 12
Project E | ET2 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 7200 | 9000 | 1800 | 120 | 150 | 30

## BY Project
Row Labels | Sum of Total Budgeted Cost | Sum of Difference
Project A | 153600 | 14550
Project B | 131100 | 4500
Project C | 216000 | 27300
Project D | 291000 | -19500
Project E | 174480 | -36240
Grand Total | 966180 | -9390

## By Project Hours
Row Labels | Sum of Total BH | Sum of Total Hour Difference
Project E | 2580 | -366
Project D | 3300 | -144
Project B | 1350 | 108
Project A | 2160 | 204
Project C | 2760 | 318
Grand Total | 12150 | 120

## By Resource
Row Labels | Sum of Difference
Larry | -42240
Inigo | -28500
Erica | -8400
Sondra | 0
Crystal | 0
Tom | 1050
Jenny | 4500
Sarah | 4500
Gail | 4800
Stanley | 7200
Jim | 8100
George | 14400
Monique | 25200
Grand Total | -9390

## By Hour Difference
Row Labels | Sum of Total BH | Sum of Total AH | Sum of Total Hour Difference
Larry | 960 | 480 | -480
Inigo | 960 | 660 | -300
Erica | 960 | 900 | -60
Sondra | 960 | 960 | 0
Crystal | 900 | 900 | 0
Tom | 960 | 990 | 30
Jenny | 960 | 1020 | 60
Sarah | 960 | 1020 | 60
Jim | 960 | 1050 | 90
Gail | 930 | 1026 | 96
Stanley | 720 | 864 | 144
George | 960 | 1200 | 240
Monique | 960 | 1200 | 240
Grand Total | 12150 | 12270 | 120

## Cost By Resource
Row Labels | Sum of Total Actual Cost
Tom | 34650
Larry | 42240
Stanley | 43200
Sondra | 43200
Gail | 51300
Inigo | 62700
George | 72000
Jenny | 76500
Sarah | 76500
Jim | 94500
Crystal | 108000
Monique | 126000
Erica | 126000
Grand Total | 956790